## Sheet1
PO No. | Plant | Product | Spec, Dimension | Order Status | Order Qty | Receiving Inspection Qty | Shipping Qty | TNC Due Date | ETD Due Date | Note
Q152714-01 | Kumamoto Plant | New Mold,Jig | CZ10006A0AMB0 NO.5 | Already received PO from TNC | 1 | 1 | 1 | 2017-02-10
Q152714/1-01 | Kumamoto Plant | New Mold,Jig | CZ10006A0AMB0 NO.6 | Waiting for shipping | 1 | 1 | 1 | 2017-02-10 | 2017-04-19
T004493-01(S)Q159214-02 | Fukushima Plant | New Mold,Jig | XH01391-L0A | Waiting for shipping | 3 | 3 |  | 2017-02-28 | 2017-04-19
T004495-01(S)Q159213-02 | Fukushima Plant | New Mold,Jig | XH01127-M0A00 | Waiting for shipping | 3 |  |  | 2017-03-31
Q158190-01 | Fukushima Plant | Remedy (Mold) | XH0685F-MA0 NO.1 | Trial finished | 1 | 1 | 1 | 2017-02-16
Q157979-01 | Fukushima Plant | Remedy (Mold) | XZ01563-E-MA3 CAV.NO.36 | Mold making finished | 1 | 1 | 1 | 2017-01-26
T004493-01 | Fukushima Plant | Initial Made Product | XH01391-L0A00 |  | 1 |  |  | 2017-02-02
Q159214-01 | Fukushima Plant | New Mold,Jig | XH01391-L0A00 | Design finished and issued PO to maker | 1 | 1 |  | 2017-01-26
Q159214(N)-01 | Fukushima Plant | New Mold,Jig | XH01391-L0A | Trial finished | 1 | 1 |  | 2017-01-26
Q159214-02 | Fukushima Plant | Initial Made Product | XH01391-L0A | Already received PO from TNC | 2 |  |  | 2017-02-15
T004495-01 | Fukushima Plant | Initial Made Product | XH01127-M0A00 | Mold making finished | 1 |  |  | 2017-02-15
Q159213-02 | Fukushima Plant | Initial Made Product | XH01127-M0A00 |  | 2 |  |  | 2017-02-15 | 2017-04-19
Q159213-01 | Fukushima Plant | New Mold,Jig | XH01127-M0A00 | Already received PO from TNC | 2 | 2 |  | 2017-01-26 | 2017-04-19
Q157976-01 | Kitaibaraki Plant | Remedy (Mold) | GN9773V0-MA0 NO.1 |  | 1 |  |  | 2017-03-22 | 2017-04-19
Q157978-01 | Kitaibaraki Plant | Remedy (Mold) | GN9535V3-MA0 NO.1 | Trial finished | 1 |  |  | 2017-03-22 | 2017-04-19
Q157980-01 | Shizuoka Plant | Remedy (Mold) | EV1734T0-MC0 NO.2 | Waiting for shipping | 1 |  |  | 2017-03-29 | 2017-04-19