## Sheet1
PO No. | Plant | Product | Spec, Dimension | Order Status | Order Qty | Receiving Inspection Qty | Shipping Qty | Due Date | ETD Due Date | Note
Q148925-01 | KUMAMOTO | ADD NEW MOLD 1 SET = NO.31 | EZ6108Z1-MA0 No.32 | Mold making finished | 1 | 1 |  | 2017-02-15
Q149013-01 | KUMAMOTO | ADD NEW MOLD 1 SET = NO.86 | EZ6041Z1-MB1 No.86 | Mold making finished | 1 | 1 |  | 2017-02-07
Q148957-01 | KUMAMOTO | ADD NEW MOLD 1 SET = NO.31 | CZZ066A0-MC0 No.31 | Mold making finished | 1 | 1 | 1 | 2016-12-23
Q148931-01 | KUMAMOTO | ADD NEW MOLD 1 SET = NO.32 | EZ6108Z1-MA0 No.31 | Mold making finished | 1 | 1 |  | 2017-02-08
Q150535-01 | TOTTORI | MOLD REMEDY | RB01102AM000 NO.1 | Design finished and issued PO to maker | 1 |  |  | 2017-07-07
Q152028-01 | KUMAMOTO | REPAIR MOLD 1 SET = NO.3 | CZ10025A0AMA0 NO.3 | Mold making finished | 1 | 1 | 1 | 2017-01-31
Q152683-01 | KUMAMOTO | ADD NEW MOLD 1 SET = NO.5 | CG00146Z0AMB1 NO.5 | Mold making finished | 1 | 1 |  | 2017-04-13
Q152680-01 | SHIZUOKA | ADD NEW MOLD 1 SET = NO.6 | EE2907T0-MC0 NO.6 | Mold making finished | 1 | 1 |  | 2017-04-17
Q152684-01 | KUMAMOTO | ADD NEW MOLD 1 SET = NO.4 | EV0539A0-MA0 NO.4 | Mold making finished | 1 | 1 |  | 2017-02-01
Q152716-01 | KUMAMOTO | ADD PUNCH SET ( 1 INNER, 1 OUTER / 7 PCS EACH / TOTAL 7 PCS ) | CZ06753-Z0 | Already received PO from TNC | 1