## Format (2)
PO No. | Plant | Product | Spec, Dimension | Order Status | Order Qty | Receiving Inspection Qty | Shipping Qty | Due Date | ETD Due Date | Note
Q148925-01 | KUMAMOTO | ADD NEW MOLD 1 SET = NO.31 | EZ6108Z1-MA0 No.32 | Mold making finished | 1 | 1
Q149013-01 | KUMAMOTO | ADD NEW MOLD 1 SET = NO.86 | EZ6041Z1-MB1 No.86 | Mold making finished | 1 | 1
Q148957-01 | KUMAMOTO | ADD NEW MOLD 1 SET = NO.31 | CZZ066A0-MC0 No.31 | Shipped | 1 | 1 | 1
Q148931-01 | KUMAMOTO | ADD NEW MOLD 1 SET = NO.32 | EZ6108Z1-MA0 No.31 | Mold making finished | 1 | 1
Q150535-01 | TOTTORI | MOLD REMEDY | RB01102AM000 NO.1 | Design finished and issued PO to maker | 1 |  |  | 2017-07-07
Q152028-01 | KUMAMOTO | REPAIR MOLD 1 SET = NO.3 | CZ10025A0AMA0 NO.3 | Shipped | 1 | 1 | 1
Q152683-01 | KUMAMOTO | ADD NEW MOLD 1 SET = NO.5 | CG00146Z0AMB1 NO.5 | Shipped | 1 | 1 | 1
Q152680-01 | SHIZUOKA | ADD NEW MOLD 1 SET = NO.6 | EE2907T0-MC0 NO.6 | Mold making finished | 1 | 1
Q152684-01 | KUMAMOTO | ADD NEW MOLD 1 SET = NO.4 | EV0539A0-MA0 NO.4 | Mold making finished | 1 | 1
Q152716-01 | KUMAMOTO | ADD PUNCH SET ( 1 INNER, 1 OUTER / 7 PCS EACH / TOTAL 7 PCS ) | CZ06753-Z0 | Design finished and issued PO to maker | 1 |  |  | 2017-07-05
Q152944/4-01 | KUMAMOTO | ADD NEW MOLD 5 SET = NO.23,24,25,26,27 | CZZ064A0-MB0 NO.27 | Shipped | 1 | 1 | 1
Q156125-01 | SHIZUOKA | ADD NEW MOLD 1 SET = NO.7 | EE2940T0-MC0 NO.7 | Mold making finished | 1 | 1
Q156125-02 | SHIZUOKA | ADD NEW MOLD 1 SET = NO.8 | EE2940T0-MC0 NO.8 | Mold making finished | 1 | 1
Q156121-01 | KUMAMOTO | ADD NEW MOLD 1 SET =NO.80 | EZ6607Z1-MA3 NO.80 | Already received PO from TNC | 1
Q156152-01 | TOTTORI | MOLD REMEDY | RT0037AM000 NO.1 | Mold making finished | 1 | 1
Q157972-01 | KUMAMOTO | ADD NEW MOLD 1 SET = NO.2 | EV10029Z0AMA0 NO.2 | Design finished and issued PO to maker | 1 |  |  | 2017-06-02
Q157978-01 | KITA-IBARAKI | SEND MOLD REMEDY | GN9535V3-MA0 NO.1 | Design finished and issued PO to maker | 1 |  |  | 2017-07-05
Q158834-01 | SHIZUOKA | ER0353T0-MC0 NO.1 | ER0353-T0 NO.1 | Design finished and issued PO to maker | 1 |  |  | 2017-08-26
Q158834-02 | SHIZUOKA | ER0353N0-MA0 NO.2 | ER0353-T0 NO.2 | Design finished and issued PO to maker | 1 |  |  | 2017-09-05
Q158837-01 | SHIZUOKA | ER0922T0-MA0 NO.1 | ER0922-T0 NO.1 | Mold making finished | 1 | 1
Q158837-02 | SHIZUOKA | ER0922T0-MA0 NO.2 | ER0922-T0 NO.2 | Mold making finished | 1 | 1
Q158838-01 | SHIZUOKA | ER0966T0-MA0 NO.1 | ER0966-T0 NO.1 | Design finished and issued PO to maker | 1 |  |  | 2017-08-25
Q158838-02 | SHIZUOKA | ER0966T0-MA0 NO.2 | ER0966-T0 NO.2 | Design finished and issued PO to maker | 1 |  |  | 2017-08-25
Q158840-01 | SHIZUOKA | ER0931T0-MA1 NO.1 | ER0931-T0 NO.1 | Shipped | 1 | 1 | 1
Q158840-02 | SHIZUOKA | ER0931T0-MB0 NO.3 | ER0931-T0 NO.3 | Shipped | 1 | 1 | 1
Q158842-01 | SHIZUOKA | ER0890N1-MA0 NO.1 | ER0890-T0 NO.1 | Design finished and issued PO to maker | 1 |  |  | 2017-07-14
Q158842-02 | SHIZUOKA | ER0890N1-MA0 NO.2 | ER0890-T0 NO.2 | Design finished and issued PO to maker | 1 |  |  | 2017-07-14
Q158843-01 | SHIZUOKA | ER0879T0-MA0 NO.1 | ER0879-T0 NO.1 | Design finished and issued PO to maker | 1 |  |  | 2017-07-26
Q158843-02 | SHIZUOKA | ER0879T0-MA0 NO.2 | ER0879-T0 NO.2 | Design finished and issued PO to maker | 1 |  |  | 2017-07-27
Q158844-01 | SHIZUOKA | ER01054-T0A-MA0 NO.1 | ER01054-T0 NO.1 | Design finished and issued PO to maker | 1 |  |  | 2017-07-21
Q158844-02 | SHIZUOKA | ER01054-T0A-MA0 NO.2 | ER01054-T0 NO.2 | Design finished and issued PO to maker | 1 |  |  | 2017-07-24
Q158835-01 | SHIZUOKA | ER01046-T0A-MA0 NO.2 | ER01046-T0 NO.2 | Design finished and issued PO to maker | 1 |  |  | 2017-07-24
Q160666-01 | FUKUSHIMA | RETAINER PLATE | XH01438G0A00 | Mold making finished | 1 | 1
Q160277-01 | TOTTORI | MOLD REMEDY | RT0030AM010 NO2 | Mold making finished | 1 | 1
Q161526-01 | KUMAMOTO | MOLD 8 CAV. | AKJ925C301,OR 89.5x2.0 | Already received PO from TNC | 3
Q161747-01 | TOTTORI | MOLD REMEDY | RG1030AM020 CAV.NO.11 | Shipped | 1 | 1 | 1
Q162319-01 | KUMAMOTO | SEND MOLD TO NOK FOR MODIFY MOLD GAP=NO.10 | CZ5976Z0-MC1 NO.10 | Mold making finished | 1 | 1
Q162319-02 | KUMAMOTO | SEND MOLD TO NOK FOR MODIFY MOLD GAP=NO.11 | CZ5976Z0-MC1 NO.11 | Already received PO from TNC | 1
Q161626-01 | KUMAMOTO | ADD NEW MOLD NEW DESIGN 1 SET = NO.3 | MCOT110H11 NO.3 | Shipped | 1 | 1 | 1
Q161627-01 | KUMAMOTO | ADD NEW MOLD NEW DESIGN 1 SET = NO.5 | MCOT086M03 NO.5 | Shipped | 1 | 1 | 1
Q161628-01 | KUMAMOTO | ADD NEW MOLD 1 SET = NO.32 | CZ3509A0-ME1 NO.32 | Shipped | 1 | 1 | 1
Q161628-02 | KUMAMOTO | ADD NEW MOLD 1 SET = NO.33 | CZ3509A0-ME1 NO.33 | Shipped | 1 | 1 | 1
Q162470-01 | KUMAMOTO | ADD NEW MOLD ALK TYPE 1 SET =NO.3 | CO0407U0AMA1X NO.3 (ALK) | Shipped | 1 | 1 | 1
Q162471-01 | KUMAMOTO | ADD NEW MOLD ALK TYPE 1 SET =NO.7 | MCOT109H04 NO.7 (ALK) | Shipped | 1 | 1 | 1
Q162473-01 | KUMAMOTO | ADD NEW MOLD ALK TYPE 1 SET=NO.5 | MCOT090H02 NO.5 | Shipped | 1 | 1 | 1
Q162478-01 | KUMAMOTO | ADD NEW MOLD NEW DESIGN 1 SET=NO.4 | MCO0600A73 NO.4 | Shipped | 1 | 1 | 1
Q160092-01 | SHIZUOKA | ER0992-T0 (NO.3) | ER0992-T0 NO.3 | Already received PO from TNC | 1
Q160091-01 | SHIZUOKA | ER0793-T0 (NO.3) | ER0793-T0 NO.3 | Already received PO from TNC | 1
Q160084-01 | SHIZUOKA | ER0869-T0 (NO.4) | ER0869-T0 NO.4 | Design finished and issued PO to maker | 1 |  |  | 2017-09-22
Q160085-01 | SHIZUOKA | ER0389-T0 (NO.12) | ER0389-T0 NO.12 | Design finished and issued PO to maker | 1 |  |  | 2017-09-06
Q160086-01 | SHIZUOKA | ER0622-T0 (NO.24) | ER0622-T0 NO.24 | Design finished and issued PO to maker | 1 |  |  | 2017-09-11
Q160087-01 | SHIZUOKA | ER00967-T0 (NO.3) | ER00967-T0 NO.3 | Design finished and issued PO to maker | 1 |  |  | 2017-09-18
Q160088-01 | SHIZUOKA | ER00873-T0 (NO.7) | ER00873-T0 NO.7 | Design finished and issued PO to maker | 1 |  |  | 2017-09-12
Q160089-01 | SHIZUOKA | ER1014-T0 (NO.3) | ER1014-T0 NO.3 | Already received PO from TNC | 1
Q160090-01 | SHIZUOKA | ER0809-T0 (NO.5) | ER0809-T0 NO.5 | Already received PO from TNC | 1
Q163763-01 | KUMAMOTO | ADD NEW PUNCH JIG 1 SET | EV0469-A0 | Already received PO from TNC | 1
Q164158-01 | TOTTORI | MOLD REMEDY | RG01133AM004 NO.5 | Shipped | 1 | 1 | 1
Q164157-01 | FUKUSHIMA | SEND MOLD REMEDY | BH6382F-MA0 NO.1 | Already received PO from TNC | 1
Q165341-01 | KUMAMOTO | ADD NEW MOLD NEW DESIGN 1 SET =NO.4 | MCO0017R82T NO.4 | Shipped | 1 | 1 | 1
Q165756-01 | SHIZUOKA | MOLD REMEDY | ER0828T0-MB0 NO.7 | Design finished and issued PO to maker | 1 |  |  | 2017-08-10
Q165758-01 | KUMAMOTO | REPAIR MOLD 1 SET =NO.11 | CZ5785A0-MI1 NO.11 | Design finished and issued PO to maker | 1 |  |  | 2017-08-14
Q165738-01 | KUMAMOTO | REPAIR MOLD 1 SET=NO.27 | CZ3509A0-ME0 NO.27 | Mold making finished | 1 | 1
Q166098-01 | KUMAMOTO | ADD NEW PUNCH JIG 2 SET | EV0307A0-MB0 | Design finished and issued PO to maker | 1 |  |  | 2017-07-07
Q166098/1-01 | KUMAMOTO | ADD NEW PUNCH JIG 2 SET | EV0307A0-MB0 | Design finished and issued PO to maker | 1 |  |  | 2017-07-07
Q165783-01 | KUMAMOTO | ADD NEW MOLD 1 SET =NO.34 | CZ3509A0-ME1 NO.34 | Mold making finished | 1 | 1
Q165783-02 | KUMAMOTO | ADD NEW MOLD 1 SET =NO.35 | CZ3509A0-ME1 NO.35 | Mold making finished | 1 | 1
Q166936-01 | KUMAMOTO | ADD NEW MOLD 2 SET = NO.20,21 | CZZ084A0-ME0 NO.20 | Shipped | 1 | 1 | 1
Q166941-01 | KUMAMOTO | ADD NEW MOLD 2 SET = NO.24,25 | CZ6437A0-MD0 NO.24 | Mold making finished | 1 | 1
Q168348-01 | TOTTORI | MOLD | RD2279AM010 | Mold making finished | 1 | 1
Q168348-02 | TOTTORI | CUTTING JIG | RD2279AME10 | Mold making finished | 1 | 1
Q167580-01 | SHIZUOKA | PART WEAR | ER0389T0-MD0 NO.11 | Design finished and issued PO to maker | 1 |  |  | 2017-09-05
Q167426-01 | SHIZUOKA | MOLD REMEDY | ER0622T0-ME0 NO.19 | Shipped | 1 | 1 | 1
Q166914-01 | SHIZUOKA | MOLD REMEDY | ER0421T0-MB0 NO.7 | Shipped | 1 | 1 | 1
Q166913-01 | TOTTORI | MOLD REMEDY | RG01132AM003 NO.12 | Mold making finished | 1 | 1
Q167460-01 | TOTTORI | MOLD REMEDY | RG1030AM029 NO.15 | Design finished and issued PO to maker | 1 |  |  | 2017-06-21
Q166942-01 | TOTTORI | MOLD REMEDY | RF0077AM021 NO.8 | Mold making finished | 1 | 1
Q167453-01 | TOTTORI | MOLD REMEDY | RG1087AM002 NO.4 | Mold making finished | 1 | 1
Q167483-01 | TOTTORI | MOLD REMEDY | RG01132AM003 NO.7 | Mold making finished | 1 | 1
Q167915-01 | KUMAMOTO | ADD NEW MOLD 1 SET NO.22 | CZZ084A0-ME0 NO.22 | Mold making finished | 1 | 1
Q167581-01 | KUMAMOTO | ADD NEW PUNCHING JIG 1 SET | CZZ066A00 | Shipped | 1 | 1 | 1
Q168162-01 | KUMAMOTO | ADD NEW MOLD 1 SET NO.2 | CZ5926A0-MA0 NO.2 | Already received PO from TNC | 1
Q168163-01 | KUMAMOTO | ADD NEW MOLD 1 SET NO.2 | CZ3903A00 NO.2 | Design finished and issued PO to maker | 1 |  |  | 2017-07-28
Q168192-01 | KUMAMOTO | ADD NEW MOLD 1 SET NO.2 | CZ5902A0-MA1 NO.2 | Already received PO from TNC | 1
Q168161-01 | KUMAMOTO | Add new mold 1 set no.3 | CZ5714A0-MB1 NO.3 | Already received PO from TNC | 1
Q168160-01 | KUMAMOTO | ADD NEW MOLD 1 SET NO.4 | CZ3271A1-MB0 NO.4 | Design finished and issued PO to maker | 1 |  |  | 2017-08-02
Q168357-01 | KUMAMOTO | ADD NEW MOLD 1 SET NO.2 | CZ5119A0-MA0 NO.2 | Already received PO from TNC | 1
Q168356-01 | KUMAMOTO | ADD NEW MOLD 1 SET NO.8 | CZ3979A0-MA1 NO.8 | Design finished and issued PO to maker | 1 |  |  | 2017-07-21
Q168394-01 | KUMAMOTO | ADD NEW MOLD 1 SET NO.4 | CZ5234A0-MC0 NO.4 | Already received PO from TNC | 1
Q168395-01 | KUMAMOTO | ADD NEW MOLD 1 SET NO.7 | EZ7705Z0-MD0 NO.7 | Already received PO from TNC | 1
Q168351-01 | KUMAMOTO | ADD NEW MOLD 1 SET NO.4 | CZ5021A1-MA4 NO.4 | Already received PO from TNC | 1
Q168353-01 | KUMAMOTO | ADD NEW MOLD 1 SET NO.2 | CZ5924Z0-MA0 NO.2 | Design finished and issued PO to maker | 1 |  |  | 2017-07-14
Q168397-01 | KUMAMOTO | ADD NEW MOLD 2 SET NO.8,9 | EV0307A0-MB0 NO.8 | Already received PO from TNC | 1
Q168397/1-01 | KUMAMOTO | ADD NEW MOLD 2 SET NO.8,9 | EV0307A0-MB0 NO.9 | Already received PO from TNC | 1
Q168358-01 | TOTTORI | MOLD REMEDY | RG1072AM013 NO.19 | Already received PO from TNC | 1
Q168359-01 | TOTTORI | MOLD REMEDY | RT40000AM000 NO.2 | Design finished and issued PO to maker | 1 |  |  | 2017-07-13
Q168281-01 | FUKUSHIMA | SEND MOLD REMEDY | BH3152P-MA0 NO.2 | Shipped | 1 | 1 | 1
Q168651-01 | KUMAMOTO | ADD NEW MOLD 8 SET NO.32-39 | CZZ066A0-MC0 NO.32 | Design finished and issued PO to maker | 1 |  |  | 2017-07-27
Q168544-01 | KUMAMOTO | ADD NEW MOLD 1 SET | EV0539A0-MA0 NO.4 | Mold making finished | 1 | 1
Q168544-02 | KUMAMOTO | ADD NEW PUNCHING JIG 1 SET | EV0539A0-MA0 | Shipped | 1 | 1 | 1
Q168543-01 | KUMAMOTO | ADD NEW MOLD 1 SET NO.6 | CZ5809A0-MB0 NO.6 | Already received PO from TNC | 1
Q168543-02 | KUMAMOTO | ADD NEW PUNCHING JIG 1 SET | CZ5809A0-MB0 | Already received PO from TNC | 1
Q168542-01 | KUMAMOTO | ADD NEW MOLD 1 SET NO.7 | CZ5809A0-MB0 NO.7 | Already received PO from TNC | 1
Q168542-02 | KUMAMOTO | ADD NEW PUNCHING JIG 1 SET | CZ5809A0-MB0 | Already received PO from TNC | 1
Q168009-01 | TOTTORI | MOLD REMEDY | RF1502AM021 NO.7 | Mold making finished | 1 | 1
Q168010-01 | TOTTORI | MOLD REMEDY | RK01071AM000 NO.1 | Mold making finished | 1 | 1
Q168349-01 | KUMAMOTO | ADD NEW MOLD 2 SET NO.31,32 | CZ6189A1-MF1 NO.31 | Design finished and issued PO to maker | 1 |  |  | 2017-07-27
Q168349/1-01 | KUMAMOTO | ADD NEW MOLD 2 SET NO.31,32 | CZ6189A1-MF1 NO.32 | Design finished and issued PO to maker | 1 |  |  | 2017-07-28
Q169170-01 | SHIZUOKA | MOLD REMEDY | ER0622T0-MF0 NO.22 | Design finished and issued PO to maker | 1 |  |  | 2017-09-22
Q169687-03 | FUKUSHIMA | TRIM TAS70B | XH00979-H0A00 | Shipped | 1 | 1 | 1
Q169687-04 | FUKUSHIMA | GREASE JIG | XH00979-H0A00 | Shipped | 1 | 1 | 1
Q169687-05 | FUKUSHIMA | DIE 45TON 30T | XH00979-H0A00 | Shipped | 1 | 1 | 1
T004736-01 | KITA-IBARAKI | MOLD | FK10018-V2A00 | Shipped | 1 | 1 | 1
Q169167-01 | FUKUSHIMA | SEND MOLD REMEDY | XZ01563-E-MA3 NO.23,34,36 | Already received PO from TNC | 3
Q169162-01 | FUKUSHIMA | SEND MOLD REMEDY | XZ00162-F-MA0 NO.11,13 | Shipped | 2 | 2 | 2
Q169171-01 | TOTTORI | MOLD REMEDY | RG01133AM004 NO.12 | Design finished and issued PO to maker | 1 |  |  | 2017-07-21
Q169172-01 | TOTTORI | MOLD REMEDY | RG1072AM013 NO.2 | Already received PO from TNC | 1
Q169172/1-01 | TOTTORI | MOLD REMEDY | RG1072AM013 NO.13 | Design finished and issued PO to maker | 1 |  |  | 2017-07-21
Q169657-01 | KUMAMOTO | ADD NEW PUNCHING JIG 1 SET | CG0071-Z0 | Already received PO from TNC | 1
Q170096-01 | KUMAMOTO | MOLD | CZ06672-Z0A00 | Design finished and issued PO to maker | 1 |  |  | 2017-07-21
Q170097-01 | KUMAMOTO | MOLD | CZ06671-Z0A00 | Design finished and issued PO to maker | 1 |  |  | 2017-07-12
Q168348/1-01 | TOTTORI | MOLD | RD2279AM010 | Design finished and issued PO to maker | 1 |  |  | 2017-06-20
Q168348/1-02 | TOTTORI | CUTTING JIG | RD2279AME10 | Mold making finished | 1 | 1
Q169687(N)-03 | FUKUSHIMA | TRIM TAS70B | XH00979-H0A00 | Shipped | 1 | 1 | 1
Q168348(N)-01 | TOTTORI | MOLD | RD2279AM010-SR NO.2 | Mold making finished | 1 | 1
Q170401-01 | FUKUSHIMA | ADD MOLD CAVITY 22 - 30 | XZ1329-E0A NO.22~30 | Already received PO from TNC | 9
Q170400-01 | FUKUSHIMA | ADD MOLD CAVITY 22-30 | XZ1492-E0A NO.22~30 | Already received PO from TNC | 9
Q170398-01 | TOTTORI | ADD MOLD 1 SET. | RB01115AM000 | Mold making finished | 1 | 1
Q170397-01 | TOTTORI | ADD MOLD 1 SET. | RB01102AM000 | Design finished and issued PO to maker | 1 |  |  | 2017-06-28
Q170395-01 | TOTTORI | ADD MOLD 1 SET. | RB6588AM000 | Design finished and issued PO to maker | 1 |  |  | 2017-08-22
Q170394-01 | TOTTORI | ADD MOLD 1 SET | RK01074AM000 | Design finished and issued PO to maker | 1 |  |  | 2017-07-24
Q170393-01 | TOTTORI | ADD MOLD 1 SET. | RK01073AM000 | Design finished and issued PO to maker | 1 |  |  | 2017-07-24
Q170396-01 | TOTTORI | ADD MOLD 1 SET. | RB6000AM000 | Design finished and issued PO to maker | 1 |  |  | 2017-06-28
Q169600-01 | TOTTORI | MOLD REMEDY | RG1072AM013 NO.7 | Design finished and issued PO to maker | 1 |  |  | 2017-08-04
Q170343-01 | FUKUSHIMA | SEND MOLD REMEDY | EZZ052A0-MA0 NO.5 | Design finished and issued PO to maker | 1 |  |  | 2017-07-06
Q170344-01 | FUKUSHIMA | SEND MOLD REMEDY | EZZ052A0-MA0 NO.2 | Design finished and issued PO to maker | 1 |  |  | 2017-07-06
Q170377-01 | KUMAMOTO | ADD NEW MOLD 2 SET NO.4,5 | ED1422Z0-MA2 NO.4 | Design finished and issued PO to maker | 1 |  |  | 2017-07-17
Q170376-01 | KUMAMOTO | ADD NEW MOLD 1 SET NO.3 | EV0598Z0-MA2 NO.3 | Design finished and issued PO to maker | 1 |  |  | 2017-07-17
Q170374-01 | KUMAMOTO | ADD NEW PUNCH 1 SET | CO60006D0APA1X | Mold making finished | 1 | 1
Q170373-01 | KUMAMOTO | ADD NEW PUNCH ALK TYPE 1 SET | CO3065N04X | Shipped | 1 | 1 | 1
Q170094-01 | KUMAMOTO | ADD NEW MOLD 1 SET NO.15 | ED0487Z0-MB1 NO.15 | Already received PO from TNC | 1
Q170093-01 | KUMAMOTO | ADD NEW MOLD ALK TYPE 1 SET NO.7 | CO3065N04X NO.7 | Mold making finished | 1 | 1
Q169662-01 | KUMAMOTO | ADD NEW MOLD 1 SET NO.14 | ED0487Z0-MB2 NO.14 | Already received PO from TNC | 1
Q169654(N)-01 | KUMAMOTO | ADD NEW PUNCH SET(INNER 7 PCS,OUTER 7 PCS,14 PCS/SET ) | EZ07661-Z0 | Design finished and issued PO to maker | 1 |  |  | 2017-06-30
Q169656(N)-01 | KUMAMOTO | ADD NEW PUNCH SET(INNER 4 PCS,OUTER 4 PCS,8 PCS/SET ) | EZ3782-Z0 | Design finished and issued PO to maker | 1 |  |  | 2017-06-30
Q169650(N)-01 | KUMAMOTO | ADD NEW PUNCH SET(INNER 5 PCS,OUTER 5 PCS,10 PCS/SET ) | EZ10002-Z0 | Design finished and issued PO to maker | 1 |  |  | 2017-06-30
Q169659(N)-01 | KUMAMOTO | ADD NEW PUNCH SET(INNER 5 PCS,OUTER 5 PCS,10 PCS/SET ) | EZ7504-Z0 | Design finished and issued PO to maker | 1 |  |  | 2017-06-30
Q169660(N)-01 | KUMAMOTO | ADD NEW PUNCH SET(INNER 7 PCS,OUTER 7 PCS,14 PCS/SET ) | CZ6753-Z0A00 | Design finished and issued PO to maker | 1 |  |  | 2017-06-30
Q169661(N)-01 | KUMAMOTO | ADD NEW PUNCH SET(INNER 5 PCS,OUTER 5 PCS, 10 PCS/SET ) | EZ07894-Z0 | Design finished and issued PO to maker | 1 |  |  | 2017-06-30
Q169652(N)-01 | KUMAMOTO | ADD NEW PUNCH SET(INNER 5 PCS,OUTER 5 PCS,10 PCS/SET ) | EZ3782-Z1 | Design finished and issued PO to maker | 1 |  |  | 2017-06-30
Q170549-01 | KUMAMOTO | ADD NEW MOLD ALK TYPE 1 SET NO.8 | CO0005A75 NO.8 | Mold making finished | 1 | 1
Q170549-02 | KUMAMOTO | ADD NEW PUNCH ALK TYPE 1 SET | CO0005A75 | Shipped | 1 | 1 | 1
Q170546-01 | KUMAMOTO | ADD NEW MOLD 2 SET NO.4,5 | CO01121H0AMA0X NO.4 | Mold making finished | 1 | 1
Q170548-01 | KUMAMOTO | ADD NEW MOLD ALK TYPE 1 SET NO.4 | COT110H01 NO.4 | Mold making finished | 1 | 1
Q170548-02 | KUMAMOTO | ADD NEW PUNCH ALK TYPE 1 SET | COT110H01 | Shipped | 1 | 1 | 1
Q170547-01 | KUMAMOTO | ADD NEW MOLD 1 SET NO.4 | COT002N01 NO.4 | Mold making finished | 1 | 1
Q170547-02 | KUMAMOTO | ADD NEW PUNCH 1 SET | COT002N01 | Shipped | 1 | 1 | 1
Q171119-01 | TOTTORI | MOLD REMEDY | RG1030AM020 NO.17 | Design finished and issued PO to maker | 1 |  |  | 2017-07-31
Q171120-01 | FUKUSHIMA | SEND MOLD REMEDY | BH6730F-MA3 NO.6 | Already received PO from TNC | 1
Q172112-01 | KUMAMOTO | MOLD | CZ10625-A0A00 | Mold making finished | 1 | 1
Q172112-03 | KUMAMOTO | PULLEY (SIZE 300 X 115 MM) | CZ10625-A0A00 | Mold making finished | 1 | 1
Q170096-02 | KUMAMOTO | MOLD | CZ06672-Z0A00 | Shipped | 1 | 1 | 1
Q170097-02 | KUMAMOTO | MOLD | CZ0667１-Z0A | Shipped | 1 | 1 | 1
Q171994-01 | SHIZUOKA | MOLD REMEDY | EZ08432-T0A-MB3 NO.4 | Already received PO from TNC | 1
Q169687(N)01-02 | FUKUSHIMA | MOLD 60TON 2RT (14 CAV.),MOLD FOR SPARE | XH00979-H0A00 | Shipped | 17 | 17 | 17
Q172682-01 | KUMAMOTO | ADD NEW MOLD 1 SET NO.3 | CO63571C0BMA0X NO.3 | Design finished and issued PO to maker | 1 |  |  | 2017-07-17
Q172676-01 | KUMAMOTO | ADD NEW MOLD 1 SET NO.8 | DO2900G00X NO.8 | Design finished and issued PO to maker | 1 |  |  | 2017-07-17
Q172681-01 | KUMAMOTO | ADD NEW MOLD ALK TYPE 2 SET NO.6,7 | DO2900G02X NO.6 | Design finished and issued PO to maker | 1 |  |  | 2017-07-17
Q172681/1-01 | KUMAMOTO | ADD NEW MOLD ALK TYPE 2 SET NO.6,7 | DO2900G02X NO.7 | Design finished and issued PO to maker | 1 |  |  | 2017-07-17
Q172681-02 | KUMAMOTO | ADD NEW PUNCH ALK TYPE 2 SET | DO2900G02X | Already received PO from TNC | 1
Q172681/1-02 | KUMAMOTO | ADD NEW PUNCH ALK TYPE 2 SET | DO2900G02X | Already received PO from TNC | 1
Q172678-01 | KUMAMOTO | ADD NEW MOLD ALK TYPE 2 SET NO.7,8 | DO1959H01X NO.7 | Design finished and issued PO to maker | 1 |  |  | 2017-07-12
Q172678/1-01 | KUMAMOTO | ADD NEW MOLD ALK TYPE 2 SET NO.7,8 | DO1959H01X NO.8 | Design finished and issued PO to maker | 1 |  |  | 2017-07-17
Q172678-02 | KUMAMOTO | ADD NEW PUNCH ALK TYPE 2 SET | DO1959H01X | Already received PO from TNC | 1
Q172678/1-02 | KUMAMOTO | ADD NEW PUNCH ALK TYPE 2 SET | DO1959H01X | Already received PO from TNC | 1
Q172674-01 | KUMAMOTO | ADD NEW PUNCH JIG 3 SET | CZZ066-A0 | Already received PO from TNC | 1
Q172674/1-01 | KUMAMOTO | ADD NEW PUNCH JIG 3 SET | CZZ066-A0 | Already received PO from TNC | 1
Q172674/2-01 | KUMAMOTO | ADD NEW PUNCH JIG 3 SET | CZZ066-A0 | Already received PO from TNC | 1
Q172807-01 | SHIZUOKA | ADD NEW MOLD NO.8, NO.9 | ER00873-T0A-MA0 NO.8 | Design finished and issued PO to maker | 1 |  |  | 2017-09-11
Q172807/1-01 | SHIZUOKA | ADD NEW MOLD NO.8, NO.9 | ER00873-T0A-MA0 NO.9 | Design finished and issued PO to maker | 1 |  |  | 2017-09-11
Q173049-01 | KUMAMOTO | MOLD | CZ10630-Z0A00 | Design finished and issued PO to maker | 1 |  |  | 2017-07-04
Q173048-01 | KUMAMOTO | MOLD | CZ10631-Z0A00 | Design finished and issued PO to maker | 1 |  |  | 2017-07-06
Q170377(N)-01 | KUMAMOTO | ADD NEW MOLD 2 SET NO.4,5 | ED1422Z0-MA2 NO.4 | Design finished and issued PO to maker | 7 |  |  | 2017-07-17
Q159765-01 | KUMAMOTO | JIG INSPECTION CHANGE DESIGN OF NEW MATERIALS CURRENT STEEL TO ALUMINUM NEW DESIGN TO HANDLES. | CZ3744-A0 | Mold making finished | 2 | 2
Q173812(S)-01,-02 | FUKUSHIMA | MOLD 110TON 3RT (12 CAV.),MOLD 110TON 3RT (SPARE) | XZ02133-E0A00 | Design finished and issued PO to maker | 39 |  |  | 2017-07-05
Q173812(S)-03,-04 | FUKUSHIMA | EJECTOR JIG,EJECTOR PLATE | XZ02133-E0A00 | Mold making finished | 2 | 2
Q173812-04 | FUKUSHIMA | EJECTOR PLATE | XZ02133-E0A00 | Already received PO from TNC | 2
Q173812-05 | FUKUSHIMA | ENCODER TRIMMING NR200(SET) | XZ02133-E0A00 | Design finished and issued PO to maker | 1 |  |  | 2017-07-14
Q173812-06 | FUKUSHIMA | MEGNETIZING JIG & INSPECTION JIG | XZ02133-E0A00 | Design finished and issued PO to maker | 1 |  |  | 2017-07-14
Q173812(N)-06 | FUKUSHIMA | MEGNETIZING JIG & INSPECTION JIG | XZ02133-E0A00 | Mold making finished | 1 | 1
Q173812-07 | FUKUSHIMA | DIE 160 TON TRANSFER | XZ02133-E0A00 | Already received PO from TNC | 1
Q173812-08 | FUKUSHIMA | VIBRATION QTY INSPECTION JIG | XZ02133-E0A00 | Already received PO from TNC | 1
Q173630-01 | TOTTORI | MOLD REMEDY | RF1401AM010 NO.5 | Already received PO from TNC | 1
Q173035-01 | SHIZUOKA | MOLD REMEDY | ER0825N1-MB2 NO.4 | Already received PO from TNC | 1
Q172809-01 | SHIZUOKA | MOLD REMEDY | CE00061-T0A-MA0 NO.1 | Already received PO from TNC | 1
Q172808-01 | SHIZUOKA | MOLD REMEDY | EZ08421-T0A-MA0 NO.53 | Already received PO from TNC | 1
Q172673-01 | KUMAMOTO | ADD NEW MOLD 1 SET | ED1420Z1-MA1 | Design finished and issued PO to maker | 1 |  |  | 2017-09-08
Q172673(N)-01 | KUMAMOTO | ADD NEW MOLD 1 SET | ED1420Z1-MA1 | Design finished and issued PO to maker | 7 |  |  | 2017-09-08
Q172673-02 | KUMAMOTO | ADD NEW DIE SET 1 SET | ED1420Z1-MA1 | Design finished and issued PO to maker | 1 |  |  | 2017-09-11
Q172671(N)-01 | KUMAMOTO | ADD NEW MOLD 1 SET | ED1422Z0-MA2 | Design finished and issued PO to maker | 7 |  |  | 2017-08-18
Q172671-01 | KUMAMOTO | ADD NEW MOLD 1 SET | ED1422Z0-MA2 | Design finished and issued PO to maker | 1 |  |  | 2017-08-18
Q172671-02 | KUMAMOTO | ADD NEW DIE SET 1 SET | ED1422Z0-MA2 | Design finished and issued PO to maker | 1 |  |  | 2017-08-24
Q172305-01 | KUMAMOTO | ADD NEW PUNCH JIG 3 SET | CZZ064-A0 | Already received PO from TNC | 1
Q172305/1-01 | KUMAMOTO | ADD NEW PUNCH JIG 3 SET | CZZ064-A0 | Already received PO from TNC | 1
Q172305/2-01 | KUMAMOTO | ADD NEW PUNCH JIG 3 SET | CZZ064-A0 | Already received PO from TNC | 1
Q172684-01 | KUMAMOTO | ADD NEW MOLD 1 SET NO.4 | CG10013Z0AMA1 NO.4 | Already received PO from TNC | 1
Q172573-01 | TOTTORI | MOLD REMEDY | RG01137AM002 NO.4 | Already received PO from TNC | 1
Q173947-01 | FUKUSHIMA | SEND MOID REMEDY | XZ00162-F-MA0 NO.4,37 | Design finished and issued PO to maker | 2 |  |  | 2017-08-10
Q169653(N/1)-01 | KUMAMOTO | ADD NEW PUNCH SET(INNER 4 PCS,OUTER 4 PCS,8 PCS/SET ) | EZ7117-A0 | Design finished and issued PO to maker | 1 |  |  | 2017-07-07
Q168396/1-01 | KUMAMOTO | ADD NEW MOLD 1 SET NO.4 | CG0071Z0-MB2 NO.4 | Mold making finished | 1 | 1
Q174477-01 | KUMAMOTO | MOLD 50 CAV. | KNB11 10006 OR11*1.9 | Already received PO from TNC | 1
Q174477(SN)-02,-03-04 | KUMAMOTO | PUNCHING JIG,SPARE NAIKEI PUNCH 5 PCS,SPARE GAIKEI PUNCH 5 PCS | KNB11 10006 OR11*1.9 | Already received PO from TNC | 1
Q174478-01 | KUMAMOTO | MOLD 32 CAV. | KNB11 10002 OR14.8*1.9 | Already received PO from TNC | 1
Q174478(SN)-02,-03-04 | KUMAMOTO | PUNCHING JIG ,SPARE NAIKEI PUNCH 4 PCS,SPARE GAIKEI PUNCH 4 PCS | KNB11 10002 OR14.8*1.9 | Already received PO from TNC | 1
Q174479-01 | KUMAMOTO | MOLD 45 CAV. | KNB11 10001 OR12.3*1.9 | Already received PO from TNC | 1
Q174479(SN)-02,-03-04 | KUMAMOTO | PUNCHING JIG ,SPARE NAIKEI PUNCH 5 PCS.,SPARE GAIKEI PUNCH 5 PCS. | KNB11 10001 OR12.3*1.9 | Already received PO from TNC | 1
Q173948-01 | FUKUSHIMA | SEND MOLD REMEDY | XZ1428E-01-MA2 NO.1 | Already received PO from TNC | 1
Q172685-01 | KUMAMOTO | ADD NEW MOLD 1 SET NO.6 | CO3366G02X NO.6 | Already received PO from TNC | 1
Q172685(N)-01 | KUMAMOTO | ADD NEW MOLD 1 SET NO.6 | CO3366G02X NO.6 | Already received PO from TNC | 1
Q174917(S)-02,-01 | FUKUSHIMA | ADD MOLD NO.4 (#4.1-4.9),ADD MOLD NO.5 (#5.1-5.9) | XG02002-E-MA0 NO.4,5 | Design finished and issued PO to maker | 2 |  |  | 2017-08-17
Q174912-01 | FUKUSHIMA | ADD CURING JIG ITEM XG02002-E | XG02002-E | Design finished and issued PO to maker | 2 |  |  | 2017-07-13
Q174912/1-01 | FUKUSHIMA | ADD CURING JIG ITEM XG02002-E | XG02002-E | Design finished and issued PO to maker | 2 |  |  | 2017-07-13
Q175180-01 | FUKUSHIMA | MAGNETIZING HEAD NO.3 = 1.2 MM | XZ02133-E0A00 | Design finished and issued PO to maker | 2 |  |  | 2017-07-14
Q175024-01 | KUMAMOTO | ADD NEW MOLD NO.2 = 1 SET | CZ06113A1AMB0 NO.2 | Already received PO from TNC | 1
Q175025-01 | KUMAMOTO | ADD NEW MOLD NO.2 = 1 SET | CZ05854A1AMA0 NO.2 | Already received PO from TNC | 1
Q175026-01 | KUMAMOTO | ADD NEW MOLD NO.3 = 1 SET | CZ3918A2-MA0 NO.3 | Already received PO from TNC | 1
Q175027-01 | KUMAMOTO | ADD NEW MOLD NO.2 = 1 SET | CZ10455A0AMA0 NO.2 | Already received PO from TNC | 1
Q175028-01 | KUMAMOTO | ADD NEW MOLD NO.3 = 1 SET | CZ10076A0AMA0 NO.3 | Already received PO from TNC | 1
Q175029-01 | KUMAMOTO | ADD NEW DIE PUNCH = 4 SET | ED1422Z0-JDA0 | Design finished and issued PO to maker | 1 |  |  | 2017-08-24
Q175029/1-01 | KUMAMOTO | ADD NEW DIE PUNCH = 4 SET | ED1422Z0-JDA0 | Design finished and issued PO to maker | 1 |  |  | 2017-08-24
Q175029/2-01 | KUMAMOTO | ADD NEW DIE PUNCH = 4 SET | ED1422Z0-JDA0 | Design finished and issued PO to maker | 1 |  |  | 2017-08-24
Q175029/3-01 | KUMAMOTO | ADD NEW DIE PUNCH = 4 SET | ED1422Z0-JDA0 | Design finished and issued PO to maker | 1 |  |  | 2017-08-24
Q175031-01 | KUMAMOTO | ADD NEW MOLD VA TYPE = 1 SET | DO02148G0AMA1X | Already received PO from TNC | 1
Q175031-03 | KUMAMOTO | ADD CENTERING JIG = 1 SET | DO02148G0AMA1X | Already received PO from TNC | 1
Q175031-02 | KUMAMOTO | ADD NEW PUNCH VA TYPE = 1 SET | DO02148G0AMA1X | Already received PO from TNC | 1
Q175031-04 | KUMAMOTO | ADD RUBBER LOADING JIG = 1 SET | DO02148G0AMA1X | Already received PO from TNC | 1
Q175030-01 | KUMAMOTO | ADD NEW MOLD 1 SET | MCO0516H11X | Already received PO from TNC | 1
Q175030-02 | KUMAMOTO | ADD NEW PUNCH 1 SET | MCO0516H11X | Already received PO from TNC | 1
Q175032-01 | KUMAMOTO | ADD NEW MOLD VA TYPE = 1 SET | CO3835N02X | Already received PO from TNC | 1
Q175032-02 | KUMAMOTO | ADD NEW PUNCH VA TYPE = 1 SET | CO3835N02X | Already received PO from TNC | 1
Q175032-03 | KUMAMOTO | ADD CENTERRING JIG = 1 SET | CO3835N02X | Already received PO from TNC | 1
Q175032-04 | KUMAMOTO | ADD RUBBER LOADING JIG = 1 SET | CO3835N02X | Already received PO from TNC | 1
T004878-01(S)Q176255-01 | FUKUSHIMA | ,MOLD 60TON 2RT (9 CAV.) | BH02051-P0A | Design finished and issued PO to maker | 12 |  |  | 2017-07-14
Q176254-01 | FUKUSHIMA | MOLD RELEASE JIG | BH02051-P0A | Design finished and issued PO to maker | 1 |  |  | 2017-07-11
Q176255(N)-02 | FUKUSHIMA | MOLD FOR SPARE | BH02051-P0A | Design finished and issued PO to maker | 1 |  |  | 2017-07-14
Q176255-02 | FUKUSHIMA | MOLD FOR SPARE | BH02051-P0A | Design finished and issued PO to maker | 1 |  |  | 2017-07-13
Q176255-03 | FUKUSHIMA | TRIM TAS 70B | BH02051-P0A | Design finished and issued PO to maker | 1 |  |  | 2017-07-13
Q173049-02 | KUMAMOTO | INSPECTION JIG (ALUMINIUM) | CZ10630-Z0A00 | Design finished and issued PO to maker | 1 |  |  | 2017-07-19
Q173049/1-02 | KUMAMOTO | INSPECTION JIG (ALUMINIUM) | CZ10630-Z0A00 | Design finished and issued PO to maker | 1 |  |  | 2017-07-19
Q173048-02 | KUMAMOTO | INSPECTION JIG (ALUMINIUM) | CZ10631-Z0A00 | Design finished and issued PO to maker | 1 |  |  | 2017-07-19
Q173048/1-02 | KUMAMOTO | INSPECTION JIG (ALUMINIUM) | CZ10631-Z0A00 | Design finished and issued PO to maker | 1 |  |  | 2017-07-19
Q172112-02 | KUMAMOTO | INSPECTION JIG (ALUMINIUM) | CZ10625-A0A00 | Design finished and issued PO to maker | 1 |  |  | 2017-07-19
Q175664-01 | FUKUSHIMA | SEND MOLD REMEDY | BH6730F-MA3 NO.10 | Design finished and issued PO to maker | 1 |  |  | 2017-08-10
Q175666-01 | FUKUSHIMA | SEND MOLD REMEDY | XZ01492-E-02-MA1 NO.21 | Already received PO from TNC | 1
Q176364-01 | KUMAMOTO | MOLD 50 CAV. | 898394-1520 | Already received PO from TNC | 1
Q176364(N)-02,-03,-04 | KUMAMOTO | PUNCHING JIG,SPARE GAIKEI PUNCH 5 PCS.,SPARE NAIKEI PUNCH 5 PCS. | 898394-1520 | Already received PO from TNC | 1
Q176363(N)-01,-02,-03 | KUMAMOTO | PUNCHING JIG,SPARE GAIKEI PUNCH 6 PCS.,SPARE NAIKEI PUNCH 6 PCS. | D61240 | Already received PO from TNC | 1
Q159764-01 | KUMAMOTO | JIG INSPECTION CHANGE DESIGN OF NEW MATERIALS CURRENT STEEL TO ALUMINUM NEW DESIGN TO HANDLES. | CZ5772A0 | Already received PO from TNC | 1
Q159763-01 | KUMAMOTO | JIG INSPECTION CHANGE DESIGN OF NEW MATERIALS CURRENT STEEL TO ALUMINUM NEW DSIGN TO HANDLES. | CZ6287Z0 | Already received PO from TNC | 1
Q159761-01 | KUMAMOTO | JIG INSPECTION CHANGE DESIGN OF NEW MATERIALS CURRENT STEEL TO ALUMINUM NEW DESIGN TO HANDLES. | CZ6017A0 | Already received PO from TNC | 1
Q159760-01 | KUMAMOTO | JIG INSPECTION CHANGE DESIGN OF NEW MATERIALS CURRENT STEEL TO ALUMINUM NEW DESIGN TO HANDLES. | CZZ044A0 | Already received PO from TNC | 1
Q159759-01 | KUMAMOTO | JIG INSPECTION CHANGE DESIGN OF NEW MATERIALS CURRENT STEEL TO ALUMINUM NEW DESIGN TO HANDLES. | CZ6339A0 | Already received PO from TNC | 1
Q159758-01 | KUMAMOTO | JIG INSPECTION CHANGE DESIGN OF NEW MATERIALS CURRENT STEEL TO ALUMINUM NEW DESIGN TO HANDLES. | CZ6340A0 | Already received PO from TNC | 1
Q159757-01 | KUMAMOTO | JIG INSPECTION CHANGE DESIGN OF NEW MATERIALS CURRENT STEEL TO ALUMINUM NEW DESIGN TO HANDLES. | CZ3641A0 | Already received PO from TNC | 1
Q159762-01 | KUMAMOTO | JIG INSPECTION CHANGE DESIGN OF NEW MATERIALS CURRENT STEEL TO ALUMINUM NEW DESIGN TO HANDLES. | CZ6005A0 | Already received PO from TNC | 1
Q161759-01 | KUMAMOTO | INSPECTION JIG CHANGE DESIGN ( ALUMINUM ) | CZ5739-A | Already received PO from TNC | 1
Q161761-01 | KUMAMOTO | INSPECTION JIG CHANGE DESIGN ( ALUMINUM ) | CZ3863-A | Already received PO from TNC | 1
Q161762-01 | KUMAMOTO | INSPECTION JIG CHANGE DESIGN ( ALUMINUM ) | CZZ025-A | Already received PO from TNC | 1
Q161764-01 | KUMAMOTO | INSPECTION JIG CHANGE DESIGN ( ALUMINUM ) | CZ5866-A | Already received PO from TNC | 1
Q161768-01 | KUMAMOTO | INSPECTION JIG CHANGE DESIGN ( ALUMINUM ) | CZ5573-A | Already received PO from TNC | 1
Q161769-01 | KUMAMOTO | INSPECTION JIG CHANGE DESIGN ( ALUMINUM ) | CZ3918-A | Already received PO from TNC | 1
Q161773-01 | KUMAMOTO | INSPECTION JIG CHANGE DESIGN ( ALUMINUM ) | CZZ082-A | Already received PO from TNC | 1
Q161775-01 | KUMAMOTO | INSPECTION JIG CHANGE DESIGN ( ALUMINUM ) | CZ5699-A | Already received PO from TNC | 1
Q161776-01 | KUMAMOTO | INSPECTION JIG CHANGE DESIGN ( ALUMINUM ) | CZ6006-A | Already received PO from TNC | 1
Q161779-01 | KUMAMOTO | INSPECTION JIG CHANGE DESIGN ( ALUMINUM ) | CZ6360-Z | Already received PO from TNC | 1
Q161780-01 | KUMAMOTO | INSPECTION JIG CHANGE DESIGN ( ALUMINUM ) | CZ5592-A | Already received PO from TNC | 1
Q161781-01 | KUMAMOTO | INSPECTION JIG CHANGE DESIGN ( ALUMINUM ) | CZ3745-A | Already received PO from TNC | 1
Q161782-01 | KUMAMOTO | INSPECTION JIG CHANGE DESIGN ( ALUMINUM ) | CZZ057-A | Already received PO from TNC | 1
Q161783-01 | KUMAMOTO | INSPECTION JIG CHANGE DESIGN ( ALUMINUM ) | CZ3864-A | Already received PO from TNC | 1
Q161784-01 | KUMAMOTO | INSPECTION JIG CHANGE DESIGN ( ALUMINUM ) | CZZ031-A | Already received PO from TNC | 1
Q161785-01 | KUMAMOTO | INSPECTION JIG CHANGE DESIGN ( ALUMINUM ) | CZ3798-A | Already received PO from TNC | 1
Q161786-01 | KUMAMOTO | INSPECTION JIG CHANGE DESIGN ( ALUMINUM ) | CZZ039-A | Already received PO from TNC | 1
Q161787-01 | KUMAMOTO | INSPECTION JIG CHANGE DESIGN ( ALUMINUM ) | CZ3931-A | Already received PO from TNC | 1
Q161788-01 | KUMAMOTO | INSPECTION JIG CHANGE DESIGN ( ALUMINUM ) | CZZ038-A | Already received PO from TNC | 1
Q161790-01 | KUMAMOTO | INSPECTION JIG CHANGE DESIGN ( ALUMINUM ) | CZ5931-A | Already received PO from TNC | 1
Q161797-01 | KUMAMOTO | INSPECTION JIG CHANGE DESIGN ( ALUMINUM ) | CZ5095-A | Already received PO from TNC | 1
Q161798-01 | KUMAMOTO | INSPECTION JIG CHANGE DESIGN ( ALUMINUM ) | CZ5151-A | Already received PO from TNC | 1
Q161799-01 | KUMAMOTO | INSPECTION JIG CHANGE DESIGN ( ALUMINUM ) | CZ5150-Z | Already received PO from TNC | 1
Q161801-01 | KUMAMOTO | INSPECTION JIG CHANGE DESING ( ALUMINUM ) | CZ5198-A | Already received PO from TNC | 1
Q161803-01 | KUMAMOTO | INSPECTION JIG CHANGE DESIGN (ALUMINUM ) | CZ5094-A | Already received PO from TNC | 1
Q161802-01 | KUMAMOTO | INSPECTION JIG CHANGE DESIGN ( ALUMINUM ) | CZ5076-A | Already received PO from TNC | 1
Q161804-01 | KUMAMOTO | INSPECTION JIG CHANGE DESIGN ( ALUMINUM ) | CZZ026-A | Already received PO from TNC | 1
Q161805-01 | KUMAMOTO | INSPECTION JIG CHANGE DESIGN ( ALUMINUM ) | CZ5761-A | Already received PO from TNC | 1
Q161806-01 | KUMAMOTO | INSPECTION JIG CHANGE DESIGN ( ALUMINUM ) | CZ5593-A | Already received PO from TNC | 1
Q161809-01 | KUMAMOTO | INSPECTION JIG CHANGE DESIGN ( ALUMINUM ) | CZ5594-A | Already received PO from TNC | 1
Q161800-01 | KUMAMOTO | INSPECTION JIG CHANGE DESIGN ( ALUMINUM ) | CZ5399-A | Already received PO from TNC | 1
Q161808-01 | KUMAMOTO | INSPECTION JIG CHANGE DESIGN ( ALUMINUM ) | CZ5310-A | Already received PO from TNC | 1
Q161810-01 | KUMAMOTO | INSPECTION JIG CHANGE DESIGN ( ALUMINUM ) | CZ5118-A | Already received PO from TNC | 1
Q161811-01 | KUMAMOTO | INSPECTION JIG CHANGE DESIGN ( ALUMINUM ) | CZ5777-A | Already received PO from TNC | 1
Q161812-01 | KUMAMOTO | INSPECTION JIG CHANGE DESIGN ( ALUMINUM ) | CZ5639-A | Already received PO from TNC | 1
Q170097-03 | KUMAMOTO | INSPECTION JIG | TL-CZ06671-Z0A00 | Already received PO from TNC | 1
Q170096-03 | KUMAMOTO | INSPECTION JIG | TL-CZ06672-Z0A00 | Already received PO from TNC | 1